## Gantt
Legend:
[5 empty] | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk
2019-03-11
Tim Wu - FYP |  | 1 |  | March | [20 empty] | April | [34 empty] | May
1 | time axis 2019-03-11 to 2019-05-10
|  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9
Milestone Description | Category | Start | No. Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
Project Logistics
Final Year Project Allocation | Milestone | 2019-03-11 | 1 | bar: Week 1 M
Other Coursework Deadlines | Low Risk | 2019-03-11 | 12
Meeting with Dr. Ciliberto | High Risk | 2019-03-21 | 1
Meeting with Dr. Ciliberto | High Risk | 2019-04-29 | 1
Interim Report Deadline | Milestone | 2019-05-10 | 1 | bar: Week 9 F
Report
Read Briefing and Implement Template | Med Risk | 2019-03-25 | 2
Write Abstract and Introduction | Low Risk | 2019-03-28 | 3
Write Background Section | High Risk | 2019-04-23 | 10
Write Implementation and Evaluation Plans | Med Risk | 2019-04-25 | 3
Write Safety and Ethics Plan | Low Risk | 2019-05-03 | 1
Revision After Feedback from supervisor | High Risk | 2019-05-06 | 5
Literature Review
Read History about Investing | Low Risk | 2019-03-26 | 4
Read about LST RNN literature | Med Risk | 2019-04-01 | 7
Read about Machine Learning in Finance | On Track | 2019-04-12 | 10
Techincal Tasks
Do Pandas Tutorials | Med Risk | 2019-04-08 | 7
Experiment with Data and Processing | Low Risk | 2019-04-18 | 10
Revise RNN from Deep Learning module | Low Risk | 2019-04-15 | 7
To add more data, Insert new rows ABOVE this one

## About
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks description, select a category of Goal, Milestone, On Track, Low Risk, Med Risk, High Risk, Progress as a percent of task completion, a Start Date and Number of days to complete the task. The Gantt chart fills in and is color coded to help distinguish the various categories. Change the display week number to change the timeline view. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. Gantt Chart About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with input messages. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. To remove these instructions from the worksheet, go to Data > Data Tools > Data Validation > Input Message and delete them.
This is the last instruction in this worksheet.