## Gantt
Legend:
[5 empty] | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk
2019-05-10
Tim Wu - FYP |  | 1 |  | May | [27 empty] | June
1 | time axis 2019-05-06 to 2019-06-28
|  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
Milestone Description | Category | Start | No. Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
Project Logistics
Interim Report Deadline | Milestone | 2019-05-10 | 1 | bar: Week 1 F
Abstract and Draft Report Deadline | Milestone | 2019-06-03 | 1 | bar: Week 5 M
Final Report Deadline | Milestone | 2019-06-20 | 1 | bar: Week 7 T
Presentations | Milestone | 2019-06-27 | 1 | bar: Week 8 T
Supervisor Meetings | Milestone | Each week | 1 | bar: Week 2 F; Week 3 F; Week 4 F; Week 5 F; Week 6 F; Week 7 F
Report
Restructure Report from Interim | Low Risk | 2019-05-10 | 3
Write Analysis and Design Sections | Med Risk | 2019-05-13 | 7
Write Implementation and Testing Sections | High Risk | 2019-05-23 | 14
Write Results and Evaluation Sections | High Risk | 2019-06-12 | 7
Design Poster | High Risk | 2019-06-22 | 5
Research
Further research about optimisation | Low Risk | 2019-05-27 | 5
Analysis and interpretation of the results | Med Risk | 2019-06-10 | 8
Techincal Tasks
Process and clean data to network ready state | Med Risk | 2019-05-13 | 7
Build and test benchmark | Med Risk | 2019-05-20 | 5
Implement preliminary model architecture | High Risk | 2019-05-10 | 10
Initial integration testing and debugging | Low Risk | 2019-05-27 | 7
Hyperparameter Optimisation | Med Risk | 2019-06-03 | 14
To add more data, Insert new rows ABOVE this one

## About
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks description, select a category of Goal, Milestone, On Track, Low Risk, Med Risk, High Risk, Progress as a percent of task completion, a Start Date and Number of days to complete the task. The Gantt chart fills in and is color coded to help distinguish the various categories. Change the display week number to change the timeline view. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. Gantt Chart About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with input messages. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. To remove these instructions from the worksheet, go to Data > Data Tools > Data Validation > Input Message and delete them.
This is the last instruction in this worksheet.